## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | Fraud Detection in Finance
PROJECT DELIVERABLE | Trained model, presentation, report
SCOPE STATEMENT | This project focuses on detecting fraudulent financial transactions using machine learning techniques applied to the IEEE-CIS Fraud Detection dataset. The scope includes data cleaning, exploratory data analysis, feature engineering, model training, evaluation, and visualization. It excludes deployment in production systems or integration with live transaction APIs. The final outcome will be a trained and evaluated model capable of distinguishing between legitimate and fraudulent transactions with high accuracy.
START DATE | END DATE | OVERALL PROGRESS
2025-09-26 | 2025-12-01 | 100%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Define project scope and objectives | Jay, Prajakta | 2025-09-21 | 2025-09-26 | 5 | Complete
Dataset selection and understanding | Jay, Prajakta | 2025-10-05 | 2025-10-15 | 10 | Complete
Report writing (Overleaf) | Jay, Prajakta | 2025-10-20 | 2025-10-25 | 5 | Complete
Data preprocessing and cleaning | Prajakta | 2025-10-27 | 2025-10-30 | 3 | Complete
Feature engineering | Jay | 2025-10-31 | 2025-11-10 | 10 | Complete
Model selection and training | Prajakta | 2025-11-11 | 2025-11-20 | 9 | Complete
Model evaluation | Jay | 2025-11-21 | 2025-11-28 | 7 | Complete
Project submission | Jay, Prajakta | 2025-12-01 | 2025-12-01 | 1 | Complete | https://github.com/jaybhuvaa/FraudBusters/tree/main#